## Dashboard
AppealForge PAC — Build, Validation, and Pilot Tracker
Metric | Value | Operating Notes
Backlog tasks | 34 | Narrow wedge: MA post-acute denial-to-appeal packets.
Open tasks | 34 | Design bar: premium clinical command center, not bland CRUD.
Done tasks | 0 | Safety bar: citation-only clinical claims; human approval before export.
High priority tasks | 26 | Codex bar: use combined tokenmax sprint, then continue/polish prompts.
Discovery calls | 0
Qualified pilots | 0
Compliance items open | 12
Critical risks | 4
14-Day Validation Target: 20 conversations → 5 qualified operators → 3 de-identified packet tests → 1 paid pilot

## Sprint Backlog
ID | Sprint | Area | Task | Priority | Status | Owner | Acceptance Criteria | Notes
T-001 | S01 | Foundation | Create Next.js 15 app with TypeScript | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-002 | S01 | Foundation | Configure Tailwind with AppealForge tokens | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-003 | S01 | Foundation | Add Prisma schema and seed script | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-004 | S01 | Foundation | Create demo auth/session guard | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-005 | S02 | Design | Build premium login page | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-006 | S02 | Design | Build dashboard KPI strip and urgent queue | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-007 | S02 | Design | Build app shell/sidebar/header | Medium | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-008 | S02 | Design | Add empty/loading/error states | Medium | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-009 | S03 | Documents | Implement document upload metadata flow | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-010 | S03 | Documents | Create deterministic synthetic extraction pipeline | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-011 | S03 | Documents | Build denial parser review screen | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-012 | S03 | Documents | Persist denial findings with citations | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-013 | S04 | Evidence | Generate criteria from denial reason | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-014 | S04 | Evidence | Build evidence map cards with status rails | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-015 | S04 | Evidence | Build source quote drawer | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-016 | S04 | Evidence | Build missing evidence checklist | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-017 | S04 | Evidence | Add reviewer status controls | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-018 | S05 | Packet | Generate packet markdown from reviewed evidence | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-019 | S05 | Packet | Implement unsupported claim blocker | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-020 | S05 | Packet | Build packet editor and warm paper preview | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-021 | S05 | Packet | Implement packet version history | Medium | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-022 | S05 | Packet | Add PDF/HTML export with draft watermark | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-023 | S06 | Outcome | Build communication log | Medium | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-024 | S06 | Outcome | Build outcome tracker | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-025 | S06 | Audit | Write audit events for sensitive actions | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-026 | S06 | Audit | Build case audit stream | Medium | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-027 | S07 | Security | Add RBAC helper and cross-org tests | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-028 | S07 | Testing | Unit tests for citation validator | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-029 | S07 | Testing | Unit tests for unsupported claim blocker | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-030 | S07 | Testing | Playwright demo flow | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-031 | S08 | Polish | Accessibility pass | Medium | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-032 | S08 | Polish | Visual polish pass against static mockup | High | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-033 | S08 | Docs | Write README and demo script | Medium | Not Started | Codex | Implemented, reviewed, tested, and documented.
T-034 | S08 | Docs | Document compliance limitations | Medium | Not Started | Codex | Implemented, reviewed, tested, and documented.

## Validation
Date | Org | Contact | Role | Facility Count | MA Denials/Month | Appeal Rate | Packet Time (hrs) | Can Provide De-ID Cases | Qualified Pilot | Notes

## Pilot ROI
Pilot ROI Calculator
Input | Value | Unit | Notes
MA denials per month | 20 | denials | Customer-specific
Current appeal rate | 25% | % | Share appealed today
Target appeal rate | 50% | % | After AppealForge
Current packet time | 2.5 | hours | Manual assembly
Target packet time | 0.5 | hours | With product
Staff hourly cost | 55 | $/hour | Loaded cost
Expected overturn rate | 50% | % | Use customer history
Avg value per successful appeal | 2500 | $ | Covered days/revenue
Monthly software cost | 4000 | $ | Pilot or SaaS fee
Output | Formula | Value
Current appealed packets | =B4*B5 | 5
Target appealed packets | =B4*B6 | 10
Packets processed after product | =C16 | 10
Monthly labor savings | =(B7-B8)*C17*B9 | 1100
Additional appeals | =C16-C15 | 5
Monthly recovery upside | =C19*B10*B11 | 6250
Total monthly value | =C18+C20 | 7350
ROI multiple | =C21/B12 | 1.8375

## Risks
Risk | Probability | Severity | Mitigation | Status | Owner
PHI leakage into logs/vendors | Medium | High | No live PHI until BAAs; log scrubbing; vendor review | Open | Security
Hallucinated clinical claims | Medium | High | Citation-only generation; unsupported claim blocker; human approval | Open | Product
Proprietary payer criteria/IP | Medium | High | Use public/general or customer-provided licensed criteria only | Open | Legal
Slow healthcare sales | High | Medium | Regional operators; historical de-ID proof; paid pilot | Open | Founder
Bland UI reduces adoption | Medium | Medium | Design polish sprint; static mockup as target | Open | Design
OCR misses evidence | Medium | Medium | Confidence indicators; manual pinning; extraction QA | Open | Engineering
Physician distrust | Medium | High | Source quote drawer and approval workflow | Open | Clinical

## Compliance
Area | Control | Required Before Live PHI | Status | Owner | Evidence/Notes
Vendor | BAA with hosting/storage | Yes | Open | Founder
Vendor | BAA with OCR/LLM vendors | Yes | Open | Founder
Security | No PHI in logs | Yes | Open | Engineering
Security | RBAC/org scoping | Yes | Open | Engineering
Security | Audit events for PHI actions | Yes | Open | Engineering
Security | Encryption at rest and in transit | Yes | Open | Engineering
AI Safety | Citation-only clinical claims | Yes | Open | Product
AI Safety | Unsupported claim blocker | Yes | Open | Engineering
Clinical | Human approval before export | Yes | Open | Clinical
Compliance | Risk analysis completed | Yes | Open | Founder
Compliance | Incident response plan | Yes | Open | Founder
Data | Retention/deletion controls | Yes | Open | Engineering